## Project_Status_Tracker
| Project Name |  |  |  | Team Lead | Team Members
Employee Maintenance System |  |  |  |  | Vishal Zadoo | Lalak Garg
Saurabh Gupta
Ashok Sharma
Shruti Agrawal
Rajat Kumar
SrNo | Week | Activity planned | Status | Remarks
1 | 1 | Creation of Login Page and Landing Pages In HTML AND CSS | Complete
|  | PseudoCode for the case study | Complete
|  | Schema of databasec tables | In Progress
|  | Client Side Validations | In Progress
2 | 2 | JavaScript Implementations for login and landing page | Complete
|  | Client Side Validations | Complete
|  | Schema of databasec tables | In Progress
Planning of creation of modules
Distribution of workforce